## Sheet2
ID | Next Step Due Date | Component/s | STAR Project Clarity Code | Summary | BBH Comment | Project Manager | Business Analyst | Tech Lead | Status | Status Scope | Status Cost | Status Schedule | Status Resource | FAPS | STAR Engine Binary | Release Type | Production Date | Release date type
SP-208 | 2017-07-01 | SonicSTAR | ETF General Infrastructure Maintenance | Oracle Bundle Patch - CRS patch |  | Lindsay Galvin |  | Sreenivasa Jois | Performance/Duration Testing |  |  |  |  | 14224 | no | Core | 2016-07-09 | Hard
SP-31 | 2016-07-22 | SonicSTAR | IRG - 575 - Oracle 12c - FAS | Oracle 12c |  | Alexandra Warren |  | Sreenivasa JoisXXX | Performance/Duration Testing |  |  |  |  | 13666 |  | Core | 2016-08-06
SP-105 | 2016-07-29 | SonicSTAR | P199 - SPR STAR | Security Issue for Star Cash Break App (INC0148089) |  | Nick O'Hara | Wojciech Halecki | Wojciech Halecki | In UAT |  |  |  |  | 13976 | no | Config | 2016-08-20 | Hard
SP-207 | 2016-06-22 | Nebula | P145 - Fund Accounting FAS | IDC Equity Comparison US Upload File Split |  | John Giorgetti | Trevor Soucy | Gomathi Gopalakrishnan | In Development |  |  |  |  | 14186 |  |  | 2016-08-20
SP-79 | 2016-06-24 | Aquila | IRG - 550 - ETF - Risk & Remediation - FAS | STAR - ETF Multishare Class | Identified additional panels and message stream changes. Panel development end date is 6/24 what puts 9/17 TPD in jeopardy. | Lukasz Milos | Anna Jaszcz |  | In Development | [6 empty] | Core | 2016-09-24 | Soft
SP-116 | 2016-06-24 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - Autopopulate |  | Alexandra Warren | Katarzyna Kozik | Karthikeyan Sundar Raj | Ready for Functional Testing |  |  |  |  | 14017 | no | Core | 2016-09-24 | Soft
SP-202 | 2016-07-04 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - Additional Schedules |  | Alexandra Warren | Katarzyna Kozik | Quynh Nguyen | Functional Testing |  |  |  |  | 13876 | no | Core | 2016-09-24 | Soft
SP-201 | 2016-07-04 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - PERL Script (Enhance script breaks files into fund level) |  | Alexandra Warren | Katarzyna Kozik | Karthikeyan Sundar Raj | Functional Testing |  |  |  |  | 14088 | no | Core | 2016-09-24 | Soft
SP-97 | 2016-07-13 | Aquila | P145 - Fund Accounting FAS | New swap stream - FAPS 13156 |  | Alexandra Warren | Katarzyna Kozik | Narendra Rathod | In UAT |  |  |  |  | 13156 |  | Core | 2016-09-24
SP-101 | 2016-07-29 | Aquila | P118 - Fund Accounting CSG Other | Add Entity to Composite and Trial Balance - FAPS 13778 |  | Alexandra Warren | Srebro, Jakub | Prashanth Bhat | Functional Testing |  |  |  |  | 13778 | no | Core | 2016-09-24 | Soft
SP-164 | 2016-08-26 | Aquila | P145 - Fund Accounting FAS | Add Clearing Broker to Trade Jrnl - FAPS 13118A |  | Alexandra Warren | Anna Jaszcz | Sergii Dziubenko | Performance/Duration Testing |  |  |  |  | 13118A | no | Core | 2016-09-24
SP-55 | 2016-08-26 | Aquila | P145 - Fund Accounting FAS | Add Clearing Broker to Open Trades - FAPS 13118A |  | Alexandra Warren | Anna Jaszcz | Rajendra Modugula | Performance/Duration Testing |  |  |  |  | 13118A | yes | Core | 2016-09-24
SP-190 | 2016-08-26 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - CAS Codes |  | Alexandra Warren | Katarzyna Kozik | Alexandru Eva | Performance/Duration Testing |  |  |  |  | 13137 | yes | Core | 2016-09-24 | Hard
SP-188 | 2016-09-23 | Aquila | IRG 625 - Enhance Income Processing - FAS | ME IO Deferral - Phase II |  | Alexandra Warren | Katarzyna Kozik | Karthikeyan Sundar Raj | Regresion Testing |  |  |  |  | 14142 | no | Core | 2016-09-24 | Hard
SP-148 |  | Aquila | P145 - Fund Accounting FAS | Create new version of Trade & Income panel to improve run time | Eng resource needed | Alexandra Warren | Katarzyna Kozik | Karthikeyan Sundar Raj | Detail Design |  |  |  |  | 14037 |  | Core | 2016-09-24 | Soft
SP-115 | 2016-06-24 | Nebula | P145 - Fund Accounting FAS | GenericAllTypes Upload Template Enhancement |  | John Giorgetti | Trevor Soucy | Gomathi Gopalakrishnan | In UAT |  |  |  |  | 13839 | no | Core | 2016-09-24
SP-113 | 2016-06-29 | Nebula | P145 - Fund Accounting FAS | Reuters 10AM OS Intraday Pricing |  | John Giorgetti | Trevor Soucy | Gomathi Gopalakrishnan | Functional Testing |  |  |  |  | 13828 | no | Core | 2016-09-24
SP-54 | 2016-09-16 | Nebula | P161 - Fund Admin - STAR | Advisory Fee Calculation Request- Non Base Tiers |  | John Giorgetti | Rajesh Pattan | Karthikeyan Sundar Raj | Regresion Testing |  |  |  |  | 12998 |  | Core | 2016-09-24 | Hard
SP-69 | 2016-06-24 | SonicSTAR | IRG - 577 - RES Replacement - FAS | RES Improve Memory Mangement | Scope - no 64 bit upgrade; no perf improvement | Alexandra Warren | Narendra Rathod | Prashanth Bhat | Functional Testing |  |  |  |  | 14049 |  | Core | 2016-09-24 | Soft
SP-204 | 2016-06-30 | SonicSTAR | IRG - 464 - SPS Key Process Performance Improvement - FAS | Trigger Class/Sector Allocation (Functional Enhancement) |  | John Giorgetti | Adam Boudreau | Karthikeyan Sundar Raj | In Development |  |  |  |  | 13122 |  | Core | 2016-09-24
SP-203 | 2016-06-30 | SonicSTAR | IRG - 464 - SPS Key Process Performance Improvement - FAS | CalcNAV UI fix |  | John Giorgetti | Adam Boudreau | Karthikeyan Sundar Raj | Functional Testing |  |  |  |  | 13122 |  | Core | 2016-09-24
SP-166 | 2016-07-01 | SonicSTAR | IRG - 464 - SPS Key Process Performance Improvement - FAS | LPO Synchronization Control - Ledger Purge |  | John Giorgetti | Adam Boudreau | Sergii Dziubenko | In Development |  |  |  |  | 7638P | no | Core | 2016-09-24 | Soft
SP-71 | 2016-06-24 | Aquila | IRG - 495 - Derivatives Processing On STAR - FAS | Derivatives Processing On STAR CFDs | The requirement for RGL (realized gain/loss) on CFDs being reflected as one cash object (net of open and close tax lot) was missed in the Design. Engine resource available from 5/24 to start analysis after which effort estimate will be provided by 6/24. 5/31 to complete PANEL development (w/o RGL). | Lukasz Milos | Srebro, Jakub | Randolph Back | In Development |  |  |  |  | 13175 | yes | Core | 2016-11-19 | Soft