## Sheet2
ID | Component/s | STAR Project Clarity Code | Summary | BBH Comment | Project Manager | Business Analyst | Tech Lead | Production Date | Status | Next Step Due Date | Status Scope | Status Cost | Status Schedule | Status Resource | FAPS | STAR Engine Binary | Release Type | Release date type
SP-208 | SonicSTAR | ETF General Infrastructure Maintenance | Oracle Bundle Patch - CRS patch |  | Alexandra Warren |  | Sreenivasa Jois | 2016-07-09 | Performance/Duration Testing | 2016-07-01 |  |  |  |  | 14224 | no | Core | Hard
SP-31 | SonicSTAR | IRG - 575 - Oracle 12c - FAS | Oracle 12c |  | Alexandra Warren |  | Sreenivasa Jois | 2016-08-06 | Performance/Duration Testing | 2016-07-22 |  |  |  |  | 13666 |  | Core
SP-105 | SonicSTAR | P199 - SPR STAR | Security Issue for Star Cash Break App (INC0148089) |  | Alexandra Warren | Wojciech Halecki | Wojciech Halecki | 2016-08-20 | In UAT | 2016-07-29 |  |  |  |  | 13976 | no | Config | Hard
SP-194 | SonicSTAR | P192 - Production Support - FAS | Ad Hoc Schedules for DDR Time Based Messages | Need to schedule QA resource | Scott Twomey | Richard Burda | Quynh Nguyen | 2016-08-20 | Functional Testing | [5 empty] | 12691 |  | Config | Soft
SP-207 | Nebula | P145 - Fund Accounting FAS | IDC Equity Comparison US Upload File Split |  | John Giorgetti | Trevor Soucy | Gomathi Gopalakrishnan | 2016-08-20 | In Development | 2016-06-22 |  |  |  |  | 14186
SP-79 | Aquila | IRG - 550 - ETF - Risk & Remediation - FAS | STAR - ETF Multishare Class | Identified additional panels and message stream changes. Panel development end date is 6/24 what puts 9/17 TPD in jeopardy. | Lukasz Milos | Anna Jaszcz |  | 2016-09-24 | In Development | 2016-06-24 | [6 empty] | Core | Soft
SP-116 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - Autopopulate |  | Alexandra Warren | Katarzyna Kozik | Karthikeyan Sundar Raj | 2016-09-24 | Ready for Functional Testing | 2016-06-24 |  |  |  |  | 14017 | no | Core | Soft
SP-202 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - Additional Schedules |  | Alexandra Warren | Katarzyna Kozik | Quynh Nguyen | 2016-09-24 | Functional Testing | 2016-07-04 |  |  |  |  | 13876 | no | Core | Soft
SP-201 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - PERL Script (Enhance script breaks files into fund level) |  | Alexandra Warren | Katarzyna Kozik | Karthikeyan Sundar Raj | 2016-09-24 | Functional Testing | 2016-07-04 |  |  |  |  | 14088 | no | Core | Soft
SP-97 | Aquila | P145 - Fund Accounting FAS | New swap stream - FAPS 13156 |  | Alexandra Warren | Katarzyna Kozik | Narendra Rathod | 2016-09-24 | In UAT | 2016-07-13 |  |  |  |  | 13156 |  | Core
SP-101 | Aquila | P118 - Fund Accounting CSG Other | Add Entity to Composite and Trial Balance - FAPS 13778 |  | Alexandra Warren | Srebro, Jakub | Prashanth Bhat | 2016-09-24 | Functional Testing | 2016-07-29 |  |  |  |  | 13778 | no | Core | Soft
SP-164 | Aquila | P145 - Fund Accounting FAS | Add Clearing Broker to Trade Jrnl - FAPS 13118A |  | Alexandra Warren | Anna Jaszcz | Sergii Dziubenko | 2016-09-24 | Performance/Duration Testing | 2016-08-26 |  |  |  |  | 13118A | no | Core
SP-55 | Aquila | P145 - Fund Accounting FAS | Add Clearing Broker to Open Trades - FAPS 13118A |  | Alexandra Warren | Anna Jaszcz | Rajendra Modugula | 2016-09-24 | Performance/Duration Testing | 2016-08-26 |  |  |  |  | 13118A | yes | Core
SP-190 | Aquila | IRG 623 - Implement Autosettlements Phase III - FAS | Autosettlements Phase III - CAS Codes |  | Alexandra Warren | Katarzyna Kozik | Alexandru Eva | 2016-09-24 | Performance/Duration Testing | 2016-08-26 |  |  |  |  | 13137 | yes | Core | Hard
SP-188 | Aquila | IRG 625 - Enhance Income Processing - FAS | ME IO Deferral - Phase II |  | Alexandra Warren | Katarzyna Kozik | Karthikeyan Sundar Raj | 2016-09-24 | Regresion Testing | 2016-09-23 |  |  |  |  | 14142 | no | Core | Hard
SP-115 | Nebula | P145 - Fund Accounting FAS | GenericAllTypes Upload Template Enhancement |  | John Giorgetti | Trevor Soucy | Gomathi Gopalakrishnan | 2016-09-24 | In UAT | 2016-06-24 |  |  |  |  | 13839 | no | Core
SP-113 | Nebula | P145 - Fund Accounting FAS | Reuters 10AM OS Intraday Pricing |  | John Giorgetti | Trevor Soucy | Gomathi Gopalakrishnan | 2016-09-24 | Functional Testing | 2016-06-29 |  |  |  |  | 13828 | no | Core
SP-54 | Nebula | P161 - Fund Admin - STAR | Advisory Fee Calculation Request- Non Base Tiers |  | John Giorgetti | Rajesh Pattan | Karthikeyan Sundar Raj | 2016-09-24 | Regresion Testing | 2016-09-16 |  |  |  |  | 12998 |  | Core | Hard
SP-69 | SonicSTAR | IRG - 577 - RES Replacement - FAS | RES Improve Memory Mangement | Scope - no 64 bit upgrade; no perf improvement | Alexandra Warren | Narendra Rathod | Prashanth Bhat | 2016-09-24 | Functional Testing | 2016-06-24 |  |  |  |  | 14049 |  | Core | Soft
SP-204 | SonicSTAR | IRG - 464 - SPS Key Process Performance Improvement - FAS | Trigger Class/Sector Allocation (Functional Enhancement) |  | John Giorgetti | Adam Boudreau | Karthikeyan Sundar Raj | 2016-09-24 | In Development | 2016-06-30 |  |  |  |  | 13122 |  | Core
SP-203 | SonicSTAR | IRG - 464 - SPS Key Process Performance Improvement - FAS | CalcNAV Functional Enhancement |  | John Giorgetti | Adam Boudreau | Karthikeyan Sundar Raj | 2016-09-24 | Functional Testing | 2016-06-30 |  |  |  |  | 13122 |  | Core
SP-166 | SonicSTAR | IRG - 464 - SPS Key Process Performance Improvement - FAS | LPO Synchronization Control - Ledger Purge |  | John Giorgetti | Adam Boudreau | Sergii Dziubenko | 2016-09-24 | In Development | 2016-07-01 |  |  |  |  | 7638P | no | Core | Soft